## Earned Value System
This is a sample of one method of measuring project progress. It measure the variance of budgeted costs and schedules to actuals.
This becomes the mechanism for making needed adjustments so that the project can be completed successfully.
TASK | STATUS IN 100% |  | TOTAL BUDGET | BCWS | BCWP | ACWP | EAC MATH | CPI | SPI | CV | CV % | SV | SV % | DAYS TO COMPLETE PRT EST | EST COST PER REMAINING DAY PRT EST | EAC BY PRT
| SCHED | COMPLTD
Develop specifications | 1 | 1 | 5000 | 5000 | 5000 | 6000 | 6000 | 0.83333 | 1 | -1000 | -20 | 0 | 0 | 0 | 0 | 6000
Prepare site | 0.33 | 0.1 | 12000 | 3960 | 1200 | 4000 | 40000 | 0.3 | 0.30303 | -2800 | -233.3333 | -2760 | -69.697 | 8 | 2000 | 20000
Construct machine | 0.2 | 0.3 | 20000 | 4000 | 6000 | 5000 | 16666.6667 | 1.2 | 1.5 | 1000 | 16.6667 | 2000 | 50 | 8 | 1875 | 20000
Electricity to site | 0.29 | 0.2 | 7000 | 2030 | 1400 | 1000 | 5000 | 1.4 | 0.68966 | 400 | 28.5714 | -630 | -31.0345 | 5 | 1200 | 7000
Install machine | 0 | 0 | 6000 | 0 | 0 | 0 | 6000 | #DIV/0! | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 4 | 1500 | 6000
Connect electricity to machine | 0 | 0 | 3000 | 0 | 0 | 0 | 3000 | #DIV/0! | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 2 | 1500 | 3000
Produce 40 gears & test | 0 | 0 | 4000 | 0 | 0 | 0 | 4000 | #DIV/0! | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 4 | 1000 | 4000
TOTAL |  |  | 57000 | 14990 | 13600 | 16000 | 80666.6667 | 0.85 | 0.90727 | -2400 | -17.6471 | -1390 | -9.2728 |  |  | 66000

## EVS
This is a sample of one method of measuring project progress. It measure the variance of budgeted costs and schedules to actuals.
This becomes the mechanism for making needed adjustments so that the project can be completed successfully.
TASK | STATUS IN 100% |  | TOTAL BUDGET | BCWS | BCWP | ACWP | EAC MATH | CPI | SPI | CV | CV % | SV | SV % | DAYS TO COMPLETE PRT EST | EST COST PER REMAINING DAY PRT EST | EAC BY PRT
| SCHED | COMPLTD
|  |  |  | 0 | 0 |  | #DIV/0! | #DIV/0! | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! |  |  | 0
|  |  |  | 0 | 0 |  | #DIV/0! | #DIV/0! | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! |  |  | 0
|  |  |  | 0 | 0 |  | #DIV/0! | #DIV/0! | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! |  |  | 0
|  |  |  | 0 | 0 |  | #DIV/0! | #DIV/0! | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! |  |  | 0
|  |  |  | 0 | 0 |  | 6000 | #DIV/0! | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! |  |  | 0
|  |  |  | 0 | 0 |  | 3000 | #DIV/0! | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! |  |  | 0
|  |  |  | 0 | 0 |  | 4000 | #DIV/0! | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! |  |  | 0
TOTAL |  |  | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! |  |  | 0